## Tech
Line # | Issue | Bug | Perf Concern | How to fix | How to test
79 | comment says Merge statement has insert, update and delete; no delete statement in the MERGE logic | M | Y | if delete statement is supposed to be there, add it in | Add a record to demo.NightlySalesStaging that doesn't exist in dbo.SalesHistory. Confirm it doesn't exist after proc is run
172 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
192 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
212 | Drop Table and recreate through SELECT INTO (rpt_Avg_Profit_Classification_Type) BUG: create table statements creates an integer. Populated by an scalar UDF that returns a money datatype. | Y | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
268 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
319 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
356 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
386 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
410 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
486 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added
| Uses NOLOCK hints Were there locking issues that this was addressing? | N | Y | remove references research to find out why this was added. If there were locking issues, do we need to set proc to run in SNAPSHOT ISOLATION instead? Is the database set to RCSI? | confirm no locking issues exist confirm no dirty reads caused data issues
246 | use of scalar function (demo.udf_CalculateNetProfit) | N | Y | need to determine if this is causing performance issues - can't go parallel, run once for every table | isolate query and compare previous query plan with one that doesn't use a UDF to verify improvement. Confirm data is the same
390 | money to decimal(3, 2) conversion BUG: conversion happens because the commission rate is decimal (3, 2) on the nightlySalesStaging table. This query also uses another table\view for data and we're only supposed to be using the one table. | Y | N | Need to rewrite query using just the NightlySalesStaging table. | capture the data created by the original query and compare to the data created by the fixed query. Confirm the calculation for the commissions is correct and make sure the conversion issue is fixed
241 | review results of sp_QuickieStore - INSERT INTO demo.rpt_Avg_Profit_Classification_Type high IO count, low number of rows returned. | N | Y | Need to look at the query plan for problem points. Check other stats for info NOTE: this is run inside a cursor. Confirm if cursor is needed | compare execution plans of before and after query to see if improvements are made. Confirm the data doesn't change

## Tech & Business + 1
Line # | Issue | Bug | Perf Concern | How to fix | How to test | Effort | Impact
79 | comment says Merge statement has insert, update and delete; no delete statement in the MERGE logic | M | Y | if delete statement is supposed to be there, add it in | Add a record to demo.NightlySalesStaging that doesn't exist in dbo.SalesHistory. Confirm it doesn't exist after proc is run | low | High - data is wrong in ALL reports if data doesn't get deleted.
172 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
192 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
212 | Drop Table and recreate through SELECT INTO (rpt_Avg_Profit_Classification_Type) BUG: create table statements creates an integer. Populated by an scalar UDF that returns a money datatype. | Y | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | Medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
268 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
319 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
356 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
386 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
410 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
486 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table
| Uses NOLOCK hints Were there locking issues that this was addressing? | N | Y | remove references research to find out why this was added. If there were locking issues, do we need to set proc to run in SNAPSHOT ISOLATION instead? Is the database set to RCSI? | confirm no locking issues exist confirm no dirty reads caused data issues | low | low to medium. If there was no locking to begin with, this would have no impact. If we were getting incorrect data with dirty reads, we need to confirm whether we need to update past data
246 | use of scalar function (demo.udf_CalculateNetProfit) | N | Y | need to determine if this is causing performance issues - can't go parallel, run once for every table | isolate query and compare previous query plan with one that doesn't use a UDF to verify improvement. Confirm data is the same | med | medium. The change should speed performance. Need to confirm other problems aren't created by it.
390 | money to decimal(3, 2) conversion BUG: conversion happens because the commission rate is decimal (3, 2) on the nightlySalesStaging table. This query also uses another table\view for data and we're only supposed to be using the one table. | Y | N | Need to rewrite query using just the NightlySalesStaging table. | capture the data created by the original query and compare to the data created by the fixed query. Confirm the calculation for the commissions is correct and make sure the conversion issue is fixed | med | medium. Need to confirm whether there was a bug to begin with and that this fixes it. Also have to confirm that the staging table has the needed data to do the calculations otherwise, we need to determine if that needs to be modified, requiring another query in the proc to be fixed as well.
241 | review results of sp_QuickieStore - INSERT INTO demo.rpt_Avg_Profit_Classification_Type high IO count, low number of rows returned. | N | Y | Need to look at the query plan for problem points. Check other stats for info NOTE: this is run inside a cursor. Confirm if cursor is needed | compare execution plans of before and after query to see if improvements are made. Confirm the data doesn't change | med | medium. This should effect speed of the proc

## Tech & Business + 2
Line # | Issue | Bug | Perf Concern | How to fix | How to test | Effort | Impact | Time to Fix | Time to Test | Need QA | Need Dev
79 | comment says Merge statement has insert, update and delete; no delete statement in the MERGE logic | M | Y | if delete statement is supposed to be there, add it in | Add a record to demo.NightlySalesStaging that doesn't exist in dbo.SalesHistory. Confirm it doesn't exist after proc is run | low | High - data is wrong in ALL reports if data doesn't get deleted. | 1 day | 1 day | Y | N
172 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
192 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
212 | Drop Table and recreate through SELECT INTO (rpt_Avg_Profit_Classification_Type) BUG: create table statements creates an integer. Populated by an scalar UDF that returns a money datatype. | Y | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | Medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
268 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
319 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
356 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
386 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
410 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
486 | Drop Table and recreate through SELECT INTO | N | Y | change DROP TABLE to TRUNCATE TABLE change SELECT INTO into INSERT INTO statement confirm table definition is correct | confirm that stored procedure still works confirm performance isn't impacted if indexes are added | low - med | low to medium. The change is simple but if there are additions made to the tables, it could have a bigger impact to reports or other queries against the table | 1-2 days, depending on the work | 1 day | Y | N
| Uses NOLOCK hints Were there locking issues that this was addressing? | N | Y | remove references research to find out why this was added. If there were locking issues, do we need to set proc to run in SNAPSHOT ISOLATION instead? Is the database set to RCSI? | confirm no locking issues exist confirm no dirty reads caused data issues | low | low to medium. If there was no locking to begin with, this should have no impact. If we were getting incorrect data with dirty reads, we need to confirm whether we need to update past data | 2 days or more, depending on locking | 1 day | Y | N
246 | use of scalar function (demo.udf_CalculateNetProfit) | N | Y | need to determine if this is causing performance issues - can't go parallel, run once for every table | isolate query and compare previous query plan with one that doesn't use a UDF to verify improvement. Confirm data is the same | med | medium. The change should speed performance. Need to confirm other problems aren't created by it. | 2 days | 1 day | Y | N
390 | money to decimal(3, 2) conversion BUG: conversion happens because the commission rate is decimal (3, 2) on the nightlySalesStaging table. This query also uses another table\view for data and we're only supposed to be using the one table. | Y | N | Need to rewrite query using just the NightlySalesStaging table. | capture the data created by the original query and compare to the data created by the fixed query. Confirm the calculation for the commissions is correct and make sure the conversion issue is fixed | med | medium. Need to confirm whether there was a bug to begin with and that this fixes it. Also have to confirm that the staging table has the needed data to do the calculations otherwise, we need to determine if that needs to be modified, requiring another query in the proc to be fixed as well. | 2 days | 1 day | Y | N
241 | review results of sp_QuickieStore - INSERT INTO demo.rpt_Avg_Profit_Classification_Type high IO count, low number of rows returned. | N | Y | Need to look at the query plan for problem points. Check other stats for info NOTE: this is run inside a cursor. Confirm if cursor is needed | compare execution plans of before and after query to see if improvements are made. Confirm the data doesn't change | med | medium. This should effect speed of the proc | 2 days | 1 day | Y | N